## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | Understand ML, DL, Transformers and LLM concepts and connect their evolution | Must | None | Project Team | 3- Completed
1 | 1 | US-02 | Collect 5–10 real company financial documents and organize annual/quarterly reports, filings and investor documents | Must | US-01 | Project Team | 3- Completed
2 | 2 | US-03 | Study annual reports, 10-K filings, earnings reports and financial statement structures | Must | US-02 | Project Team | 3- Completed
2 | 2 | US-04 | Design multi-agent architecture, orchestration flow, responsibilities and data models | Must | US-03 | Project Team | 3- Completed
2 | 2 | US-05 | Create research workspace and session management for named sessions and uploaded documents | Should | US-04 | Project Team | 3- Completed
2 | 2 | US-06 | Build Document Agent for upload, parsing, chunking, embeddings and vector indexing with seed documents | Must | US-04 | Project Team | 3- Completed
2 | 2 | US-07 | Build Extraction Agent to extract financial metrics, ratios, revenue trends and key performance numbers | Must | US-06 | Project Team | 3- Completed
3 | 3 | US-08 | Build Red Flag Agent to detect rising debt, falling margins, anomalies and auditor qualifications | Must | US-07 | Project Team | 3- Completed
3 | 3 | US-09 | Implement orchestration layer to run Document, Extraction and Red Flag agents sequentially | Must | US-08 | Project Team | 3- Completed
3 | 3 | US-10 | Validate extraction and red-flag outputs for accuracy and source faithfulness | Must | US-09 | Project Team | 3- Completed
3 | 3 | US-11 | Build Research Agent for multi-part queries, retrieval, reasoning and strict source citations | Must | US-06 | Project Team | 3- Completed
3 | 3 | US-12 | Build Comparison Agent for side-by-side company benchmarking | Should | US-07 | Project Team | 3- Completed
3 | 3 | US-13 | Develop conversational research interface for cited financial Q&A | Should | US-11 | Project Team | 3- Completed
3 | 3 | US-14 | Begin Report Agent with Executive Summary and Key Financials sections | Should | US-10 | Project Team | 3- Completed
4 | 4 | US-15 | Complete Report Agent with Red Flags, Company Comparison and Outlook sections and PDF export | Must | US-12, US-14 | Project Team | 3- Completed
4 | 4 | US-16 | Conduct end-to-end testing for collaboration, extraction, citations and report completeness | Must | US-15 | Project Team | 3- Completed
4 | 4 | US-17 | Optimize prompts, retrieval quality and orchestration reliability across varied financial documents | Must | US-16 | Project Team | 3- Completed
4 | 4 | US-18 | Deploy the completed system to a public cloud environment | Must | US-17 | Project Team | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 | 1 | Review ML, DL, Transformer and LLM concepts and document project understanding | Sep 10 | Sep 10 | Project Team | Research | 3- Completed | 4
1 | 2 | Collect and organize six company financial reports in PDF format | Sep 10 | Sep 14 | Project Team | Data Collection | 3- Completed | 3
1 | 3 | Create initial document inventory and company/year metadata | Sep 11 | Sep 14 | Project Team | Documentation | 3- Completed | 4
2 | 4 | Study annual reports, 10-K filings, earnings reports and MD&A structures | Sep 15 | Sep 16 | Project Team | Research | 3- Completed | 5
2 | 5 | Design multi-agent architecture and orchestration flow | Sep 15 | Sep 17 | Project Team | Architecture | 3- Completed | 2
2 | 1900-01-05 | Define database, document, chunk and metric data models | Sep 17 | Sep 18 | Project Team | Design | 3- Completed | 4
2 | 1900-01-06 | Implement research workspace and session management | Sep 18 | Sep 20 | Project Team | Coding | 3- Completed | 4
2 | 1900-01-07 | Implement Document Agent: upload, parsing, chunking and indexing | Sep 19 | Sep 22 | Project Team | Coding | 3- Completed | 5
2 | 1900-01-08 | Integrate seed company documents and vector storage | Sep 22 | Sep 24 | Project Team | Integration | 3- Completed | 3
2 | 1900-01-09 | Implement Extraction Agent for metrics, ratios and trends | Sep 23 | Sep 25 | Project Team | Coding | 3- Completed | 3
3 | 1900-01-10 | Implement Red Flag Agent for debt, margins, liquidity and auditor risks | Sep 26 | Sep 30 | Project Team | Coding | 3- Completed | 3
3 | 1900-01-11 | Implement multi-agent orchestration: Document → Extraction → Red Flag | Sep 29 | Oct 2 | Project Team | Coding | 3- Completed | 4
3 | 1900-01-12 | Validate extraction and red-flag results against source documents | Oct 1 | Oct 3 | Project Team | Testing | 3- Completed | 3
3 | 1900-01-13 | Implement Research Agent with multi-step retrieval and citations | Oct 2 | Oct 5 | Project Team | Coding | 3- Completed | 3
3 | 1900-01-14 | Implement Comparison Agent for peer benchmarking | Oct 4 | Oct 6 | Project Team | Coding | 3- Completed | 3
3 | 1900-01-15 | Develop conversational research UI | Oct 5 | Oct 7 | Project Team | UI | 3- Completed | 3
3 | 1900-01-16 | Begin Report Agent: Executive Summary and Key Financials | Oct 7 | Oct 11 | Project Team | Coding | 3- Completed | 3
4 | 1900-01-17 | Complete Report Agent with Red Flags, Comparison and Outlook | Oct 12 | Oct 13 | Project Team | Coding | 3- Completed | 3
4 | 1900-01-18 | Implement PDF report generation and download | Oct 13 | Oct 14 | Project Team | Coding | 3- Completed | 3
4 | 1900-01-19 | Run end-to-end test suite and validate citation accuracy | Oct 14 | Oct 15 | Project Team | Testing | 3- Completed | 3
4 | 1900-01-20 | Optimize prompts, retrieval and varied-document parsing | Oct 15 | Oct 16 | Project Team | Optimization | 3- Completed | 3
4 | 22 | Prepare deployment configuration and public cloud deployment | Oct 16 | Oct 19 | Project Team | Deployment | 2- In Progress | 5
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 10th Sep | Understanding the project scope and ML/AI concepts | Finalize learning notes and begin financial document collection
1 | 12th Sep | Finding consistent company financial reports and years | Standardize filenames and document metadata
2 | 15th Sep | Understanding the new agent architecture requirements | Break milestone into architecture, workspace, Document Agent and Extraction Agent
2 | 20th Sep | PDF parsing/chunking and vector indexing integration | Test each ingestion stage independently
3 | 26th Sep | Coordinating multiple agents sequentially | Implement orchestrator with stage-level error handling
3 | 5th Oct | Maintaining source citations across retrieval and comparison | Store source/page/chunk metadata with every extracted result
4 | 12th Oct | Final report generation and end-to-end validation | Complete PDF report, test suite and optimization
4 | 19th Oct | Public cloud deployment configuration | Correct deployment root/start command and verify public endpoint

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 10th Sep | 14th Sep | Project Team | Start structured financial document collection | Stop collecting files without metadata | Continue learning ML/AI foundations | Maintain company/year/source inventory
2 | 2 | 15th Sep | 25th Sep | Project Team | Start modular agent implementation | Stop testing individual scripts in isolation | Continue incremental integration | Run project from root and test each module
3 | 3 | 26th Sep | 11th Oct | Project Team | Add source citations during extraction | Stop allowing unsupported generated claims | Continue agent-level validation | Add citation checks to every research response
4 | 4 | 12th Oct | 19th Oct | Project Team | Run complete end-to-end tests before deployment | Stop changing deployment configuration without local validation | Continue optimization and defect tracking | Validate deployment path, start command and public endpoint