## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Project Team | 18-Sep-2026 | Python import failed when running Document Agent directly; ingestion package was not found. | Sprint 2 | Project Team | Maintainability | Added __init__.py files, standardized package names to lowercase, and instructed execution from project root via app entry point. | 19-Sep-2026 | Closed | Root-level execution verified.
2 | Project Team | 18-Sep-2026 | app.py could not import agents because VS Code Code Runner was executing with an incorrect working directory. | Sprint 2 | Project Team | Maintainability | Opened the repository root in VS Code and changed execution to python app.py from the project root. | 19-Sep-2026 | Closed | Import path verified.
3 | Project Team | 19-Sep-2026 | Vector-store test failed because the financial_documents Chroma collection had not yet been created. | Sprint 2 | Project Team | Logical | Changed test sequence so document ingestion runs first and creates the collection before querying it; use get_or_create_collection in the ingestion path. | 19-Sep-2026 | Closed | Vector store query verified after ingestion.
4 | Project Team | 19-Oct-2026 | Public deployment failed because the configured root directory did not match the repository folder structure. | Sprint 4 | Project Team | Others | Corrected the deployment root/start configuration to match the actual repository layout and application entry point. | 19-Oct-2026 | Closed | Deployment configuration corrected.
5 | Project Team | 19-Oct-2026 | Deployment configuration needed to point to the actual application entry point rather than a missing nested directory. | Sprint 4 | Project Team | Others | Updated service configuration to use the repository root and correct Python start command. | 19-Oct-2026 | Closed | Start command aligned with project structure.
6 | Project Team | 15-Oct-2026 | Financial extraction initially depended on exact metric labels, reducing robustness across varied company report wording. | Sprint 4 | Project Team | Logical | Expanded canonical metric mappings to include common synonyms such as Revenues, Net Sales and Total Revenue. | 16-Oct-2026 | Closed | Extraction supports varied metric labels.
7 | Project Team | 15-Oct-2026 | Real-world PDF formatting could break metric and financial-document phrase matching because of line breaks, extra spaces and hyphenated words. | Sprint 4 | Project Team | Logical | Added text normalization before classification, chunking and extraction. | 16-Oct-2026 | Closed | PDF normalization added to Document Agent.
8 | Project Team | 16-Oct-2026 | Non-financial documents could enter the indexing pipeline without a document-type gate. | Sprint 4 | Project Team | Logical | Added financial-document classification as a hard gate before chunking/indexing. | 17-Oct-2026 | Closed | Rejected documents no longer reach downstream agents.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others